## Sheet1
TASK | ASSIGNED TO | UI STATUS | API STATUS
Registration | Monu | Incomplete | Incomplete
Login | Monu | Incomplete | Incomplete
PNR Status | Ahsin | Incomplete | Incomplete
Train Search | Ahsin | Incomplete | Complete
Train Schedule | Ahsin | Incomplete | Complete
Train Fare | Nitin | Incomplete | Complete
Booking History | Nitin | Incomplete | Incomplete
Cancel Booking | Nitin | Incomplete | Complete
Admin Part | Shikha | Complete | Complete
Seat Availability | Shikha | Complete | Complete
Booking | Shikha | Incomplete | Incomplete
Front Screen | Shikha | Complete | No Need
Front Screen After Login As User | Shikha | Incomplete | No Need
Front Screen After Login As Admin | Shikha | Complete | No Need